ITEC630 - IT Masters Project Part A

Semester 1 - 2026

Assessment 1 - Project Management Plan

DeepMoisture: AI-Driven Soil Moisture Forecasting for Australian Agriculture

Submitted By
( SANSS )

Sudip Paudyal ( S00391778 )

Amir Tamang ( S00393664 )

Nischal Rai ( S00392579 )

Syarifah Haninah ( S00394184 )

Suhana Pradhan ( S00393735 )

Submitted to

Walayat Hussain

Word Count: 3986

Date of Submission: 5 April, 2026

Table of Contents

1. Introduction	1

1.1.	Project Overview	1

1.2. Project Deliverables	1

1.3.	Ethical Considerations and Environmental Stewardship	1

2. Project Management Methodology	2

2.1. Selected Approach	2

2.2. Justification for Approach	3

3. Team Coordination and Performance Monitoring	4

3.1. Roles and Task Delegation	4

3.2. Performance Monitoring	4

3.3. Peer Evaluation	5

3.4. Resource Calendar	5

4. Project Planning and Scheduling Strategies	6

4.1. Work Breakdown Structure (WBS)	6

4.2. Sprint Planning & Schedule Baseline	7

5. Scope Management	9

5.1. In-Scope Requirements	9

5.1.1. Functional Requirements	9

5.1.2. Non-Functional Requirements	9

5.2. Out-of-Scope Exclusions	10

5.3. Scope Change Control	10

5.4. Change Management Plan	10

6. Risk Management Plan	11

6.1. Risk Identification & Mitigation Strategies	11

7. Quality Management Plan	12

7.1. Quality Baseline & Metrics	12

7.2. Testing Strategy	13

8. Communication and Stakeholder engagement	13

8.1. Communication Protocols	13

8.2. Stakeholder Engagement	14

9. Cost Management Plan and Baseline	15

9.1. Cost Management Approach	15

9.2. Cost Baseline	15

10. Procurement Management Plan	16

10.1. Procurement Register	16

Sponsor Acceptance	17

References	18

Table of Tables

Table 1: Project Deliverables and Descriptions.	1

Table 2: Selected Approach.	2

Table 3 Justification for Approach.	3

Table 4: Roles and Task Delegation.	4

Table 5 Performance Monitoring.	5

Table 6 Resource Calendar.	5

Table 7 Sprint Planning & Schedule Baseline.	7

Table 8 Functional Requirements.	9

Table 9 Non-Functional Requirements.	9

Table 10 Out-of-Scope Exclusions.	10

Table 11 Change Management Plan.	10

Table 12 Risk Identification & Mitigation Strategies.	11

Table 13 Quality Baseline & Metrics	12

Table 14 Testing Strategy.	13

Table 15 Communication Protocol Matrix	13

Table 16 Stakeholder Engagement	14

Table 17 Cost Baseline	15

Table 18 Procurement Register.	16

Table of Figures

Figure 1 Work Breakdown Structure.

Figure 2 Gantt Chart.

# 1. Introduction

This Project Management Plan is designed to properly manage the team's software development lifecycle for this project. It will serve as an evolving document throughout the entire software development process, providing a structured framework for methodology, scope, risk, and team coordination.

## Project Overview

This project focuses on developing the Agricultural Soil Moisture Forecasting System. Accurate soil moisture tracking is a critical component of addressing the ongoing agricultural water crisis, particularly within heavily managed ecosystems like the Murray-Darling Basin. Historically, agricultural forecasting has relied on traditional statistical models (such as ARIMA), which often struggle to capture the complex, non-linear patterns of modern meteorological data. Recent developments in artificial intelligence have introduced time-series foundation models that offer unprecedented zero-shot forecasting capabilities. This project will apply formal project management principles to systematically evaluate these recent AI advancements in a real-world agricultural context, ensuring that the software development is rigorous, reproducible, and delivered within the project's constraints.

## 1.2. Project Deliverables

The successful execution of this project will result in two primary software and analytical deliverables:

Table 1: Project Deliverables and Descriptions.

| Deliverable | Description |
| --- | --- |
| Predictive Models | The deployment, fine-tuning, and evaluation of state-of-the-art time-series foundation models (specifically Chronos-2 and TimesFM). These will be rigorously benchmarked against traditional baseline models to quantify improvements in predictive accuracy. |
| Streamlit Dashboard | An interactive, front-end user interface built with Streamlit. This system will ingest meteorological data and visualize forecasting outputs, providing end-users with an accessible, highly responsive platform for agricultural decision-making. |

## Ethical Considerations and Environmental Stewardship

In alignment with the Australian Computer Society (ACS) Code of Ethics, this project prioritizes the enhancement of community well-being by addressing the ongoing agricultural water crisis. Furthermore, guided by the principles of Catholic Social Thought, the DeepMoisture system serves as a practical tool for environmental stewardship. By optimizing predictive models for soil moisture in the heavily managed Murray-Darling Basin, the project promotes the sustainable use and conservation of critical natural resources. This ensures that the system's technological advancements are inherently directed toward serving the common good and protecting the environment for future generations.

# 2. Project Management Methodology

A project management technique is a structured set of rules and practices used to effectively organize, supervise, and complete a project. It acts as a structure to help groups arrange their work to achieve the best results. To effectively manage the complexities of both software development and advanced data science, this project abandons a traditional, rigid Waterfall approach. Instead, the team is utilizing a hybrid methodology to maintain flexibility and scientific precision. [1]

## 2.1. Selected Approach

The chosen methodology is an integration of the Agile (Scrum) framework with the CRISP-DM (Cross-Industry Standard Process for Data Mining) lifecycle.[2]

Table 2: Selected Approach.

| Methodology Component | Description | Application for this Project |
| --- | --- | --- |
| Agile (Scrum) | An iterative framework focusing on continuous delivery, collaboration, and adaptability through time-boxed cycles (Sprints). | Used to manage the overall project timeline, track deliverables in Jira, and iteratively build the Streamlit dashboard UI. |
| CRISP-DM | The industry-standard lifecycle for data science consists of six phases: Business Understanding, Data Understanding, Data Preparation, Modeling, Evaluation, and Deployment. | Provides the scientific structure for handling the SILO/TERN meteorological data and rigorously evaluate the foundation models. |
| Hybrid Integration | Embedding the CRISP-DM phases into Agile Sprints. Data science milestones are treated as trackable software deliverables. | Ensure that highly experimental tasks (like AI model fine-tuning) remain on schedule and within scope boundaries. |

## 2.2. Justification for Approach

In our project, utilizing an iterative approach based on the hybrid Agile and CRISP-DM methodologies will save us time, money, and unwanted effort by focusing on building a minimal viable product (MVP) early on. Rather than perfecting each stage from the start, we will discover obstacles early on, such as data quality issues or model constraints, and solve them in later sprints. This enables us to stay on schedule and within budget while constantly upgrading the system. Developing an AI-driven forecasting system presents unique challenges that traditional project management cannot easily accommodate.[3] The hybrid Agile/CRISP-DM approach was specifically selected to address these requirements:

Table 3 Justification for Approach.

| Project Requirement | Why the Hybrid Approach | Expected Benefit |
| --- | --- | --- |
| Iterative Model Fine-Tuning | Training models like Chronos-2 and TimesFM are highly experimental. Agile allows the team to evaluate model performance (KGE/RMSE) at the end of short sprints and pivot hyperparameters quickly. | Prevents wasted time on underperforming models and ensures continuous improvement of predictive accuracy. |
| Dashboard UI/UX Development | Building a user-facing system requires continuous feedback. Agile allows for frequent beta testing of the Streamlit dashboard layout and station selectors. | Ensures high-quality user experience with a target of less than a 1% failure rate for new users. |
| Resource Constraints (Compute Limits) | The project relies on Google Colab Pro, which has strict GPU memory limits. Short, 2-week sprints force the team to frequently review resource consumption. | Prevents sudden computing overruns, allowing the team to adjust data batch sizes or processing times before running out of resources. |

# 3. Team Coordination and Performance Monitoring

Effective team coordination is essential for successfully integrating the data science and software engineering components of this forecasting system. This section outlines the strategies for task delegation and performance monitoring to ensure successful project execution.

## 3.1. Roles and Task Delegation

We have divided the key responsibilities among all our group members, assigning them specific roles and tasks to perform and be responsible for.

Table 4: Roles and Task Delegation.

| Role | Team Member | Key Responsibilities |
| --- | --- | --- |
| Project Manager | Amir Tamang | Oversees overall project execution, manages team coordination, and ensures the project remains within scope and on schedule. |
| Data Engineer | Nishchal Rai | Responsible for data acquisition pipelines (SILO/TERN APIs), exploratory data analysis (EDA), and defining the core methodology. |
| Software Developer | Suhana Pradhan | Leads system implementation, focusing on front-end integration and building the interactive Streamlit dashboard. |
| Quality & Scope Lead | Syarifah Haninah | Manages scope boundaries, identifies risks, and ensures models meet the required testing and quality baselines. |
| Communications Lead | Sudip Paudyal | Facilitates internal communication protocols, tracks sprint progress, and prepares stakeholder reporting. |

## 3.2. Performance Monitoring

The team will employ an Agile framework to continuously monitor project health and resource consumption throughout the software development process:

Table 5 Performance Monitoring.

| Monitoring Area | Tools / Framework | Purpose and Strategy |
| --- | --- | --- |
| Sprint Tracking | Kanban Board (e.g., Jira, Trello) | To track sprint velocity, monitor task bottlenecks, and ensure work package deliverables are met on time. |
| Resource Utilization | Google Colab Pro | To monitor usage hours and GPU memory allocation, preventing compute overruns during the intensive fine-tuning of foundation models (Chronos-2, TimesFM). |

## 3.3. Peer Evaluation

To ensure accountability and accurately reflect each member's efforts, peer evaluations will be integrated directly into the project lifecycle. These evaluations will be managed by the university's designated system, as explained and demonstrated at the beginning of the semester. This process guarantees that individual contributions are transparently assessed and marked accordingly by the assessor.

## 3.4. Resource Calendar

The DeepMoisture project requires all team members for the entire 12-week duration of the semester. While all project team members have committed to a standard baseline availability of 10-12 hours per week to meet ongoing project milestones, individual levels of effort will fluctuate based on the Agile Sprint schedule.

The following calendar outlines the peak utilization periods for each team member to ensure resources are available when their specific technical expertise is most required:

Table 6 Resource Calendar.

| Team Member (Role) | Standard Availability | Peak Utilization Period | Primary Focus During Peak |
| --- | --- | --- | --- |
| Amir (Project Manager) | 10-12 hrs/week | Sprints 1 & 6 (Weeks 1-2, 11-12) | Project initiation, finalizing the Assessment 3 proposal, and managing the final technical report and sponsor sign-off. |
| Nishchal (Data Engineer) | 10-12 hrs/week | Sprints 2 & 3 (Weeks 3-6) | Building the SILO/TERN data pipelines, conducting Exploratory Data Analysis (EDA), and training the ARIMA/LSTM baselines. |
| Nina (Quality Lead) | 10-12 hrs/week | Sprints 4 & 6 (Weeks 7-8, 11-12) | Monitoring foundation model fine-tuning (Chronos-2, TimesFM) against KGE metrics and leading beta testing. |
| Suhana (Software Developer) | 10-12 hrs/week | Sprints 5 & 6 (Weeks 9-12) | Developing the Streamlit dashboard wireframes, building interactive charts, and executing front-end integration. |
| Sudip (Communications Lead) | 10-12 hrs/week | Continuous (Weeks 1-12) | Facilitating weekly Jira updates, sprint reviews, and preparing the final Assessment 3 presentation materials. |

# 4. Project Planning and Scheduling Strategies

Effective project planning and scheduling are critical to ensuring the DeepMoisture forecasting system is delivered within the stipulated 14-week academic term. This project utilizes a hybrid planning strategy: a traditional Work Breakdown Structure (WBS) to define the technical scope, paired with an Agile Scrum framework to govern the execution schedule.

## 4.1. Work Breakdown Structure (WBS)

The WBS decomposes the overall project into five manageable technical phases, following a top-down approach from major deliverables to individual work packages.

- Phase 1: Initiation and Data Acquisition: Focuses on establishing the project architecture and data pipeline. Encompasses automated data collection via meteorological APIs (SILO, TERN, BoM), preprocessing, feature engineering, and dataset versioning.

- Phase 2: Baseline Execution: Involves the configuration, training, and testing of traditional statistical and deep learning models (ARIMA, XGBoost, and LSTM). This phase establishes the quantitative performance benchmark (KGE/RMSE) required for comparative analysis.

- Phase 3: Foundation Model Engineering: The core research-intensive phase. Includes the implementation of advanced time-series foundation models (Chronos-2 and TimesFM 2.5). Work packages include zero-shot inference, fine-tuning on the custom agricultural dataset, and managing cloud computer resources.

- Phase 4: System Integration: Focuses on translating backend data science into a user-friendly frontend. Involves building the Streamlit dashboard, integrating dynamic forecasting charts, and mapping station selectors.

- Phase 5: Project Closure & Evaluation: The finalization phase. Includes beta usability testing of the dashboard, codebase optimization, and the preparation of the final academic technical report and sponsor presentation.

Figure 1 Work Breakdown Structure.

## 4.2. Sprint Planning & Schedule Baseline

The execution of the WBS is managed through an Agile Scrum methodology consisting of seven two-week Sprints spanning the 14-week project lifecycle. A Jira Kanban board serves as the central platform to track sprint velocity and individual task assignments.

Table 7 Sprint Planning & Schedule Baseline.

| Sprint & Timeline | Project Phase Alignment | Key Deliverables & Activities |
| --- | --- | --- |
| Sprint 1: (Weeks 1-2) | Phase 1: Project Initiation | Finalize Assessment 1 (PMP) and Assessment 3 proposals. Set up Jira board, GitHub repository, and Google Colab Pro environments. |
| Sprint 2: (Weeks 3-4) | Phase 1: Data Engineering | Develop extraction scripts for SILO/TERN APIs. Execute Exploratory Data Analysis (EDA) and resolve missing sensor values. |
| Sprint 3: (Weeks 5-6) | Phase 2: Baseline Models | Train ARIMA and LSTM baselines. Output foundational performance metrics (KGE/RMSE) for future benchmarking. |
| Sprint 4: (Weeks 7-8) | Phase 3: Foundation Models (Zero-Shot) | Execute zero-shot configurations for Chronos-2 and TimesFM 2.5 on the Murray-Darling agricultural dataset. |
| Sprint 5: (Weeks 9-10) | Phase 3: Foundation Models (Fine-Tuning) | Conduct advanced model fine-tuning. Monitor and optimize GPU memory limits to prevent compute overruns. |
| Sprint 6: (Weeks 11-12) | Phase 4: Dashboard Integration | Develop Streamlit UI wireframes. Integrate models to display interactive forecasting charts and uncertainty bands. |
| Sprint 7: (Weeks 13-14) | Phase 5: Evaluation & Closure | Conduct beta usability testing (target <1% failure rate). Incorporate feedback, finalize the codebase, and deliver the final presentation. |

Figure 2 Gantt Chart.

# 5. Scope Management

Effective scope management ensures the project delivers exactly what is required to meet the learning outcomes and system objectives, without succumbing to "scope creep."

## 5.1. In-Scope Requirements

The project scope encompasses all tasks required to develop, train, and deploy the DeepMoisture forecasting system. These requirements are strictly divided into functional (system actions) and non-functional (system qualities) categories to dictate the system's architecture.

### 5.1.1. Functional Requirements

These define the specific behaviors and capabilities the system must execute:

Table 8 Functional Requirements.

| Requirement ID | Functional Requirement | Description |
| --- | --- | --- |
| FR-01 | Automated Data Ingestion | The system must programmatically extract historical meteorological data via SILO APIs and ground-truth soil moisture via TERN/BoM APIs. |
| FR-02 | Model Training & Inference | The system must execute preprocessing, train baseline models (ARIMA/LSTM), and run inference on time-series foundation models (Chronos-2, TimesFM). |
| FR-03 | Interactive Visualization | The Streamlit dashboard must provide end-users with dynamic station selection and visual forecasting charts. |
| FR-04 | Performance Output | The system must automatically calculate and display comparative accuracy metrics (KGE, RMSE) for all tested models. |

### 5.1.2. Non-Functional Requirements

These define the strict operational parameters and quality attributes the system must adhere to:

Table 9 Non-Functional Requirements.

| Requirement ID | Non-Functional Requirement | Description |
| --- | --- | --- |
| NFR-01 | Resource Constraints | Model fine-tuning and inference must not exceed the GPU memory allocation limits of a standard Google Colab Pro instance. |
| NFR-02 | Usability Standard | The Streamlit dashboard UI must be intuitive, with a task failure rate of <1% during peer beta testing. |
| NFR-03 | Data Integrity | All datasets and model weights must be strictly version-controlled using Data Version Control (DVC) and GitHub to ensure complete reproducibility. |
| NFR-04 | Deployment Environment | The system interface must be lightweight enough to be deployed and run locally for academic assessment and demonstration purposes. |

## 5.2. Out-of-Scope Exclusions

To ensure the project remains feasible within the 12-week timeframe and compute constraints, the following items are strictly excluded from the project boundaries:

Table 10 Out-of-Scope Exclusions.

| Excluded Item | Reason for Exclusion |
| --- | --- |
| Hardware Integration | The system will rely entirely on historical and API-driven data. Deploying physical IoT soil sensors in the field is excluded. |
| Real-Time Edge Computing | Models will be run in a cloud/local environment (Google Colab). Deploying lightweight models to edge devices is out of scope. |
| Commercial Web Hosting | The Streamlit dashboard will be deployed locally for assessment purposes. Purchasing a domain and scaling for commercial web traffic is excluded. |

## 5.3. Scope Change Control

While the overarching Change Management Plan governs general project changes (schedule/budget), changes specifically impacting the software scope must undergo the following evaluation:

- Request: A team member proposes adding or removing a system feature.

- Impact Analysis: The Quality Lead (Nina) evaluates how the scope change impacts Google Colab compute limits and model accuracy metrics.

- Approval: The Project Manager approves or denies the scope adjustment before it is escalated to the Unit Coordinator.

## 5.4. Change Management Plan

While Section 5.3 specifically governs boundaries of the software product, this overarching Change Management Plan governs any requests that impact the project’s schedule, cost baselines, or team resources. Any team member may submit a formal change request. To ensure modifications do not derail the strict 14-week timeline, the team will adhere to the following change control process:

Table 11 Change Management Plan.

| Step | Phase | Action & Responsibility |
| --- | --- | --- |
| 1 | Identify & Log | The team member identifies the need for a change and formally logs it into the project's Change Request Register (maintained within the Jira workspace). |
| 2 | Impact Analysis | The Project Manager (Amir) evaluates the proposed change to determine its specific impact on the Agile Sprint schedule, team workload, and cloud computing resources. |
| 3 | Board Review | The request analyzed is submitted to the Change Control Board (CCB). In the context of this academic project, the CCB comprises the project team and the Unit Coordinator/Sponsor. |
| 4 | Implementation | If formally approved by the CCB, the Project Manager updates the Jira timeline, adjusts the necessary baselines, and communicates the updated objectives to the team during the next Sprint Planning session. |

# 6. Risk Management Plan

The approach to managing risks for the DeepMoisture project involves a methodical process of identifying, ranking, and mitigating potential threats to the system's success. Given the experimental nature of time-series foundation models, proactive risk management is critical to maintaining the 14-week schedule.

## 6.1. Risk Identification & Mitigation Strategies

The project team has identified the most likely technical and project-level risks. The following table outlines these risks, their potential impact, and the proactive mitigation strategies the team will employ:

Table 12 Risk Identification & Mitigation Strategies.

| Risk Category | Identified Risk | Impact Level | Mitigation Strategy |
| --- | --- | --- | --- |
| Technical Risk | GPU Memory & Compute Limits: Fine-tuning Chronos-2 and TimesFM 2.5 exceeds the memory allocation limits of Google Colab Pro. | High | The Quality Lead will aggressively monitor resource consumption. If limits are approached, the team will reduce data batch sizes, utilize gradient accumulation, or fall back to zero-shot inference only. |
| Technical Risk | Data Pipeline Failures: SILO or TERN APIs experience downtime, or historical datasets contain significant missing sensor values. | Medium | The Data Engineer will build robust error-handling into the extraction scripts and implement advanced data imputation techniques (e.g., forward-filling, interpolation) during the EDA phase. |
| Project Risk | Performance Shortfalls: The foundation models fail to outperform the traditional ARIMA and LSTM baselines in KGE/RMSE metrics. | Medium | If foundation models underperform, the team will utilize a hybrid ensemble approach or pivot the final report to analyze why traditional models succeeded in this specific context, ensuring academic validity regardless of the outcome. |
| Project Risk | Schedule Slippage: Streamlit dashboard integration takes longer than the allocated Sprint 6 timeline. | Low | The team will adopt a Minimum Viable Product (MVP) approach. The core forecasting charts will be prioritized first, with secondary features (like advanced station filtering) moved to a project backlog. |

# 7. Quality Management Plan

The Quality Management Plan ensures that the DeepMoisture forecasting system meets both the academic rigor required for time-series forecasting and the functional usability required for an interactive software application. Quality will be managed continuously throughout the Agile Sprints.

## 7.1. Quality Baseline & Metrics

To objectively measure success, the project relies on specific quantitative baselines. Foundation models (Chronos-2, TimesFM) must be rigorously benchmarked against traditional baselines (ARIMA, LSTM) to prove their viability.

The Quality Lead (Nina) will monitor the following core metrics:

Table 13 Quality Baseline & Metrics

| Quality Domain | Metric | Target Baseline / Acceptance Criteria |
| --- | --- | --- |
| Model Accuracy | Kling-Gupta Efficiency (KGE) | Foundation models must achieve a KGE score greater than the ARIMA baseline on the test dataset. |
| Error Rate | Root Mean Square Error (RMSE) | Foundation models must demonstrate a lower RMSE compared to traditional statistical baselines. |
| Dashboard Usability | Task Failure Rate | New users interacting with the Streamlit dashboard must experience a task failure rate of < 1% when selecting stations or rendering forecasting charts. |

## 7.2. Testing Strategy

The team will employ a structured testing methodology tailored to the unique challenges of time-series data and interactive web deployment:

Table 14 Testing Strategy.

| Testing Phase | Testing Methodology | Purpose |
| --- | --- | --- |
| Data Validation | Temporal Data Splitting | Traditional random splits leak future data in time-series forecasting. Data will be strictly separated into chronological Train/Validation/Test splits to prevent data leakage. |
| Model Benchmarking | Comparative Evaluation | Running identical historical meteorological datasets through both the baseline models and the fine-tuned foundation models to objectively compare KGE/RMSE outputs. |
| System Testing | Beta Usability Testing | Before final submission, the Streamlit dashboard will undergo peer beta testing to identify UI bugs, broken station filters, or slow chart rendering times. |

# 8. Communication and Stakeholder engagement

A proper communication strategy with effective stakeholder engagement is one of the critical success factors in IT projects. Project failures are often linked with poor information flow and unmanaged stakeholder expectations. Thus, our project, spanning a five-member distributed team and a project supervisor, will be equipped with a structured communication plan that will ease the decision-making process and eventually guarantee transparency and accountability throughout.

## 8.1. Communication Protocols

A communication framework shall be adopted in alignment with the Agile methodology as described in the earlier section of the plan. Here, communication channels are separated out by various key factors like audience, urgency, and formality. The following table summarizes the protocols set.

Table 15 Communication Protocol Matrix

| Channel | Audience | Frequency | Format | Owner |
| --- | --- | --- | --- | --- |
| Sprint Review | The entire team and the supervisor | Bi-weekly (EOD Sprint) | Demo and Jira report | Project Lead |
| Daily Stand-up | Core team (5 members) | Daily (async via Slack) | text update | Rotating |
| Progress Report | Academic Supervisor | Weeks 5, 9, 13 | PDF milestone summary | Project Lead |
| Sprint Retrospective | Core team | Bi-weekly | Structured debrief document | Scrum Master |
| Email / MS Teams | Supervisor / Sponsor | As required | Formal written record | Project Lead |

Sprint-level tasks in the project will be managed in Jira, which ensures shared and auditable logs, unlike mechanisms like story points and sprint velocity. Slack will be the primary channel for daily standups, chats, and informal coordination. The delivery of formal entities, such as milestone reports, is to be submitted to the supervisor via Teams or email. This will help in maintaining a documented communication record in alignment with PMBOK guidance on information management.

## 8.2. Stakeholder Engagement

Stakeholder identification and engagement are to be based on the PMBOK stakeholder management framework. This framework classifies stakeholders as per their level of interest and influence.

Four primary stakeholders have been identified for our project. The following Table presents the Stakeholder information with their respective engagement strategies.

Table 16 Stakeholder Engagement

| Stakeholder | Interest | Influence | Engagement Level | Strategy |
| --- | --- | --- | --- | --- |
| Academic Supervisor | Research quality, timely delivery | High (grade authority) | Manage Closely | Bi-weekly reviews |
| Project Team (×5) | Workload balance, learning | High (execution) | Lead / Collaborate | Daily stand-ups and Jira |
| ACU Course Coordinator | Academic compliance, rubric | Medium (assessment) | Keep Informed | Milestone reports |
| Murray-Darling Farmers (end users) | Practical irrigation value | Low (indirect) | Monitor | Dashboard prototype demo |

The supervisor in this project holds the strongest influence as the primary assessor, who is set to be engaged via formal bi-weekly reviews. Project teams are concerned with operation and workload balance through collaboration. These processes are managed via daily standups and Jira ticketing systems. Likewise, the course coordinator will be kept well informed via milestone reports. The end user of this project, the farmers of the Murray-Darling Basin, are downstream stakeholders whose practical needs are addressed by the Streamlit dashboard, though they are engaged indirectly through the project requirements. Significant communications relating to scope change requests, milestone decisions, etc., shall be documented in Jira and reported to the supervisor, in accordance with the responsible project management practices.

# 9. Cost Management Plan and Baseline

## 9.1. Cost Management Approach

The Project Manager will be responsible for managing and reporting on the project’s costs. Because this is an academic research project, the primary financial constraints are cloud computing resources and API access limits, alongside the simulated labor hours of the project team. Financial performance will be tracked using earned value metrics, and any variances exceeding 10% of the allocated compute budget will require a review of data batch sizes and GPU allocation to prevent overruns.

## 9.2. Cost Baseline

The cost baseline for the DeepMoisture project includes all simulated labor hours and estimated infrastructure costs for the successful completion of the system.

Table 17 Cost Baseline

| Project Phase | Total budget | Comments |
| --- | --- | --- |
| Planning & Architecture | $4,000 | Includes 80 combined work hours for project planning, methodology definition, and UI wireframing. |
| Data Engineering | $3,200 | Includes 60 labor hours for EDA and ETL pipeline creation, plus hypothetical commercial licensing for SILO/TERN API tier access. |
| Model Development & Fine-Tuning | $5,500 | Includes 100 labor hours for coding, plus the required Google Colab Pro / Pro+ subscription costs for extended GPU computer instances. |
| System Integration & Testing | $3,000 | Includes 60 labor hours for Streamlit dashboard development, beta testing, and quality assurance. |
| Project Closeout | $2,000 | Includes 40 labor hours for finalizing the technical report and obtaining formal sponsor acceptance. |
| Total Estimated Baseline | $17,700 | Simulated commercial budget for the 12-week development lifecycle. |

# 10. Procurement Management Plan

The Project Manager will provide oversight for all procurement activities. For the DeepMoisture project, physical hardware procurement is excluded from the scope. However, the team must procure essential digital resources, software subscriptions, and data access rights to successfully execute the system build.

The Project Manager will ensure these digital resources are acquired before their necessary Agile Sprints and will track any associated subscription costs against the established project baseline.

## 10.1. Procurement Register

Table 18 Procurement Register.

| Digital Resource | Procurement Justification | Required Timeline |
| --- | --- | --- |
| SILO & TERN API Keys | Developer access keys are required to authenticate the data ingestion pipeline for historical meteorological and ground-truth soil moisture datasets. | Must be procured before Sprint 2 (Data Engineering). |
| Google Colab Pro Subscriptions | Upgraded computer instances are required to secure adequate GPU memory allocation for fine-tuning the Chronos-2 and TimesFM foundation models. | Must be procured before Sprint 4 (Foundation Model Engineering). |
| GitHub / DVC Storage | Appropriate repository storage limits must be secured to handle the version control of large datasets and model weights. | Must be procured before Sprint 1 (Project Initiation). |

# Sponsor Acceptance

By signing below, the Project Sponsor formally accepts the Project Management Plan for the DeepMoisture Agricultural Soil Moisture Forecasting System.

Approved by the Project Sponsor:

Date:

Walayat Hussain

# References

[1] Teamwork, “Project Management Methodologies – Everything You Need To Know,” www.teamwork.com, Feb. 26, 2020. https://www.teamwork.com/project-management-guide/project-management-methodologies/

[2] Asaad Abdollazadeh, Ph.D, “A common question by data scientists concerned about project management and delivery, is what is difference between CRISP-DM and Agile methodology. I share my experience and understanding of the two in here.,” Linkedin.com, May 18, 2021. http://linkedin.com/pulse/crisp-dm-agile-scrum-methodology-data-science-project-abdollazadeh (accessed Apr. 04, 2026).

[3] S. Lima, “Why an Iterative Approach Results in Successful Data Science Projects,” InfoWorks, Feb. 03, 2023. https://www.infoworks-tn.com/resources/why-an-iterative-approach-results-in-successful-data-science-projects/

[4] Queensland Government, "SILO - Australian climate data from 1889 to yesterday," Department of Environment and Science. [Online]. Available:

[5] Y. Mohanty, "Predicting Droughts: A Comparative Study of ARIMAX, LSTM, XGBoost, and Random Forest Models," 2025.

[6] A. F. Ansari et al., "Introducing Chronos-2: From univariate to universal forecasting," 2025.

[7] Project Management Institute, A Guide to the Project Management Body of Knowledge (PMBOK Guide), 7th ed. Newtown Square, PA: Project Management Institute, 2021.

[8] K. Schwalbe, Information Technology Project Management, 9th ed. Boston, MA: Cengage Learning, 2023.