## Slide 1
DeepMoisture
Sensing tomorrow's soil, today.
PROJECT MANAGEMENT PLAN
AI-Driven Soil Moisture
Forecasting for Australian
Agriculture
A Project Management Plan for benchmarking zero-shot foundation models against fine-tuned deep-learning baselines on Murray-Darling Basin soil-moisture data.
ITEC630 • IT Masters Project Part A • Semester 1, 2026
TEAM SANSS
Sudip Paudyal · Amir Tamang · Nischal Rai · Syarifah Haninah · Suhana Pradhan
Submitted to: Walayat Hussain
Australian Catholic University

## Slide 2
Agenda
What we'll walk you through over the next 15 minutes
01
Project Overview
Why this project, and why now
02
Technical Requirements
Functional & non-functional specs
03
Methodology
Hybrid Agile + CRISP-DM
04
Scope & WBS
What's in, what's out
05
Schedule & Sprints
7 sprints, 14 weeks
06
Team & Resources
5 members, clear roles
07
Risk & Quality
What could go wrong, and our plan
08
Communication & Cost
Stakeholders, channels, budget
09
MVP Demonstration
Why we built a working prototype
10
Key Takeaways
What we want you to remember
DeepMoisture • ITEC630 • Team SANSS
2 / 18

## Slide 3
Project Overview
Why is forecasting soil moisture in the Murray-Darling Basin worth solving?
40%
of Australia's farm output
1M km²
Murray-Darling Basin
23%
farm profit drop in drought
The Problem
Traditional ARIMA and statistical models struggle to capture the non-linear extremes of Australian climate — and that's where farmers need them most.
Deep learning (LSTM) works, but it demands huge local datasets and weeks of fine-tuning. That's a real barrier for academic and farm-level deployment.
And foundation models? They've been hyped on academic benchmarks since 2024 — but no one has rigorously tested them on Murray-Darling soil moisture under real Australian climate extremes.
That's the gap we close.
Our Solution: DeepMoisture
A head-to-head benchmark — managed under a hybrid Agile+CRISP-DM framework — answering one clean research question:
Can zero-shot foundation models match (or beat) fine-tuned baselines on real Australian agricultural data?
• Zero-shot Chronos-2 + TimesFM 2.5 — no local training needed.
• Tuned ARIMA, XGBoost, LSTM baselines for honest comparison.
• A Streamlit dashboard delivering forecasts + uncertainty bands to farmers.
DeepMoisture • ITEC630 • Team SANSS
3 / 18

## Slide 4
Technical Requirements — System Architecture
A four-layer pipeline: data in, forecasts out
Course scope reminder: ITEC630 is graded on the project-management plan itself — but Team SANSS also built a working MVP to prove every requirement is genuinely buildable within constraints.
LAYER 01
Data Ingestion
SILO • TERN • BoM APIs
Pulls climate, soil-moisture, and streamflow data via REST and OGC web services.
LAYER 02
Processing
pandas • NumPy • DVC
Temporal alignment, gap-filling, feature engineering, versioned train/val/test splits.
LAYER 03
Model Layer
Chronos-2 • TimesFM • PyTorch
Runs zero-shot and fine-tuned foundation models against ARIMA, XGBoost and LSTM baselines.
LAYER 04
Presentation
Streamlit • Plotly
Interactive dashboard with station selection, forecast charts, and uncertainty bands.
Modular by design — each layer can be swapped, tested, or upgraded independently. That's how we keep risk low.
DeepMoisture • ITEC630 • Team SANSS
4 / 18

## Slide 5
Functional Requirements — What the System Must Do
13 requirements, prioritised using MoSCoW — here are the eight that drive our build
ID
Requirement
Description
Priority
FR-01
Automated Data Ingestion (SILO)
Pull daily rainfall, temperature, ET, humidity from SILO REST API for 10+ MDB stations.
MUST
FR-02
Soil-Moisture Target (TERN SMIPS)
Download daily volumetric soil moisture from TERN at 1 km grid resolution.
MUST
FR-05
Preprocessing Pipeline
Align all sources to daily resolution, perform QC, fill gaps <3 days via linear interpolation.
MUST
FR-07
Baseline Models
Implement persistence, climatology, ARIMA, XGBoost, and LSTM as comparison baselines.
MUST
FR-08
Foundation Models — Zero-Shot
Run Chronos-2 and TimesFM 2.5 with no local training; produce probabilistic forecasts.
MUST
FR-09
Foundation Models — Fine-Tuned
Fine-tune both models on Australian data with weather covariates.
MUST
FR-11
Evaluation Framework
Compute KGE, RMSE, MAE, NSE, R², PBIAS, CRPS at all horizons; Diebold-Mariano tests at p < 0.05.
MUST
FR-12
Streamlit Dashboard
Station-selection map, time-series plots with uncertainty bands, model comparison, CSV export.
MUST
Every requirement above has measurable acceptance criteria — no requirement is 'done' until its test passes. Full MoSCoW set (FR-01 → FR-13) in the project plan document.
DeepMoisture • ITEC630 • Team SANSS
5 / 18

## Slide 6
Non-Functional Requirements — How the System Must Behave
Quality attributes turn a working system into a trustworthy one
NFR-01
Performance
Inference for all stations within 5 minutes on single GPU.
NFR-02
Scalability
Add stations via YAML — zero code changes required.
NFR-03
Reproducibility
100% reproducible runs via DVC + fixed random seeds.
NFR-04
Reliability
API retry logic with exponential backoff; zero silent failures.
NFR-05
Usability
<1% task failure rate for new users in peer beta testing.
NFR-06
Security
API keys in environment variables; zero credentials in Git history.
NFR-07
Portability
Single conda env runs on Linux, macOS, and Windows.
NFR-08
Maintainability
PEP-8 compliant; ≥60% test coverage; Google-style docstrings.
Why does this matter? Because evaluators — and ultimately the farmers we want to help — only trust forecasts they can run, repeat, and verify for themselves.
DeepMoisture • ITEC630 • Team SANSS
6 / 18

## Slide 7
Data Sources & Technology Stack
Open, government-grade data — paired with state-of-the-art open-source tools
AUSTRALIAN GOVERNMENT DATA SOURCES
SILO Climate
Queensland Government
Rainfall, temperature, ET, humidity — daily, ~5 km grid since 1889.
TERN SMIPS
Terrestrial Ecosystem Research Network
Daily volumetric soil moisture at three depth layers, 1 km grid.
TERN CosmOz
Cosmic-ray neutron sensors
Ground-truth soil moisture at 16+ Australian sites for validation.
BoM Water Online
Bureau of Meteorology
Streamflow & storage from ~3,500 hydrological stations.
OPEN-SOURCE TECHNOLOGY STACK
Modelling
Chronos-2 (Amazon) • TimesFM 2.5 (Google) • PyTorch • XGBoost
Data
Python 3.11 • pandas / NumPy • DVC for data versioning
Frontend
Streamlit • Plotly • Streamlit Cloud (free tier)
Ops
Jira (Scrum board) • GitHub + Actions CI/CD • Google Colab Pro (GPU)
DeepMoisture • ITEC630 • Team SANSS
7 / 18

## Slide 8
Methodology — Hybrid Agile + CRISP-DM
Why one framework wasn't enough
Pure Agile struggles with the experimental nature of ML modelling. Pure CRISP-DM lacks Agile's discipline. We embed CRISP-DM phases inside Agile sprints — getting iteration speed AND scientific rigour.
AGILE SCRUM
Project execution layer
7 sprints × 2 weeks (14-week semester total)
Tracked in Jira with capability-based backlog
Daily async stand-ups via Slack
Bi-weekly Sprint Reviews with our Supervisor
Sprint Retrospectives — continuous improvement
Story-point velocity to forecast workload
CRISP-DM LIFECYCLE
Data-science scientific layer
Business Understanding — research question framing
Data Understanding — SILO/TERN exploratory analysis
Data Preparation — QC, gap-filling, feature engineering
Modelling — baselines, then foundation models
Evaluation — KGE, RMSE, statistical significance tests
Deployment — Streamlit dashboard for end-users
= Each CRISP-DM phase becomes a trackable, time-boxed Jira deliverable.
DeepMoisture • ITEC630 • Team SANSS
8 / 18

## Slide 9
Scope & Work Breakdown Structure
Five phases, clear boundaries — so nothing slips through the cracks
DeepMoisture
1.0
Initiation & Data
1.1 SILO/TERN API setup
1.2 EDA & data QC
1.3 Feature engineering
1.4 DVC versioning
2.0
Baseline Models
2.1 ARIMA training
2.2 XGBoost training
2.3 LSTM training
2.4 KGE/RMSE benchmark
3.0
Foundation Models
3.1 Chronos-2 zero-shot
3.2 TimesFM zero-shot
3.3 Fine-tuning loop
3.4 GPU optimisation
4.0
Integration
4.1 Streamlit wireframes
4.2 Forecast charts
4.3 Station selector
4.4 Uncertainty bands
5.0
Closure
5.1 Beta testing
5.2 Final report
5.3 Sponsor sign-off
5.4 Code archival
OUT OF SCOPE: physical IoT hardware • real-time edge computing • commercial web hosting • satellite imagery purchase
DeepMoisture • ITEC630 • Team SANSS
9 / 18

## Slide 10
Schedule — 7 Sprints, 14 Weeks
Time is our least flexible constraint — so every sprint has a clear deliverable
Sprint
Weeks
Phase
Key Deliverables
Timeline (W1 → W14)
S1
W1–2
Initiation
PMP finalised, Jira board live, GitHub repo, Colab environments ready
S2
W3–4
Data Engineering
SILO/TERN extraction scripts, EDA notebook, missing-data handling
S3
W5–6
Baselines
ARIMA + LSTM trained; first KGE/RMSE benchmark numbers in W&B
S4
W7–8
Zero-Shot FM
Chronos-2 + TimesFM running zero-shot on MDB stations
S5
W9–10
Fine-Tuning
Fine-tuned weights converged; GPU memory monitored & optimised
S6
W11–12
Dashboard
Streamlit UI wireframes → interactive charts → uncertainty bands
S7
W13–14
Closure
Beta testing (<1% failure target), final report, presentation
Key Milestones: M1 PMP signed off (W2) • M2 Data pipeline live (W4) • M3 Baselines benchmarked (W6) • M4 FM fine-tuned (W10) • M5 Dashboard MVP (W12) • M6 Final delivery (W14)
DeepMoisture • ITEC630 • Team SANSS
10 / 18

## Slide 11
Team SANSS — Five Members, Five Specialisations
Roles built around the project's natural fault lines: PM, data, modelling, frontend, comms
Amir Tamang
S00393664
Project Manager
Oversees execution, manages coordination, keeps us on scope and on schedule.
Peak:
Sprints 1 & 6
Nischal Rai
S00392579
Data Engineer
Owns SILO/TERN data pipelines, exploratory analysis, and core methodology.
Peak:
Sprints 2 & 3
Suhana Pradhan
S00393735
Software Developer
Leads system implementation and the interactive Streamlit dashboard.
Peak:
Sprints 5 & 6
Syarifah Haninah
S00394184
Quality & Scope Lead
Manages scope boundaries, identifies risks, enforces quality baselines.
Peak:
Sprints 4 & 6
Sudip Paudyal
S00391778
Communications Lead
Internal comms, sprint progress tracking, stakeholder reporting.
Peak:
Continuous (W1-12)
Standard availability: 10–12 hrs/week each, with role-specific peaks aligned to Agile sprint rhythm.
DeepMoisture • ITEC630 • Team SANSS
11 / 18

## Slide 12
Risk Management — Identify Early, Mitigate Decisively
Four risks we're actively watching, with concrete fall-back plans
R-01 TECHNICAL
GPU memory limits on Colab
PROB
High
IMPACT
High
MITIGATION
Aggressively monitor consumption. If approached: reduce batch sizes, use gradient accumulation, or fall back to zero-shot inference only.
R-02 TECHNICAL
Data pipeline / API downtime
PROB
Medium
IMPACT
Medium
MITIGATION
Robust error-handling with exponential backoff in extraction scripts; forward-fill and interpolation for missing sensor values.
R-03 PROJECT
Foundation models underperform baselines
PROB
Medium
IMPACT
Medium
MITIGATION
Pivot the report to analyse WHY traditional models won in this context — academically valid either way. Hybrid ensemble as plan B.
R-04 PROJECT
Schedule slippage on dashboard
PROB
Low
IMPACT
Medium
MITIGATION
MVP-first approach: core forecasting charts ship in Sprint 6; advanced filtering moves to backlog if time runs short.
DeepMoisture • ITEC630 • Team SANSS
12 / 18

## Slide 13
Quality Management — How We Prove It Works
Quality isn't a checkbox — it's the metrics we hit and the tests we pass
Model Accuracy
KGE (Kling-Gupta Efficiency)
→ Foundation > ARIMA baseline
RMSE (Root Mean Square Error)
→ Foundation < ARIMA RMSE
CRPS (probabilistic skill)
→ Calibrated uncertainty bands
Diebold-Mariano test
→ Statistical significance @ p < 0.05
System Quality
Code style
→ PEP-8 compliant, flake8 clean
Test coverage
→ ≥60% on core modules
Reproducibility
→ 100% reproducible via DVC
Documentation
→ Google-style docstrings everywhere
Dashboard UX
Task failure rate
→ <1% in peer beta testing
Load time
→ Dashboard renders in <5 seconds
Interactive elements
→ Station map, charts, CSV export
Accessibility
→ Clear labels, minimal jargon
TESTING STRATEGY: Temporal data splitting (no leakage) • Comparative model benchmarking • Beta usability testing • W&B experiment tracking
DeepMoisture • ITEC630 • Team SANSS
13 / 18

## Slide 14
Communication & Stakeholders
Right channel, right cadence, right audience — every time
COMMUNICATION CHANNELS
Daily Stand-up (Slack)
Daily, async • Team (×5)
Sprint Review
Bi-weekly (EOD) • Team + Supervisor
Milestone Report
W5, W9, W13 • Supervisor + Coordinator
Jira Board
Continuous • Team
Sprint Retrospective
Bi-weekly • Core team
STAKEHOLDER ENGAGEMENT MAP
HIGH INFLUENCE →
LOW INFLUENCE
Supervisor
Manage Closely
Project Team
Lead/Collaborate
ACU Coordinator
Keep Informed
MDB Farmers (end users)
Monitor
DeepMoisture • ITEC630 • Team SANSS
14 / 18

## Slide 15
Jira Dashboard
DeepMoisture • ITEC630 • Team SANSS
14 / 18

## Slide 16
Cost & Procurement
An academic project — minimal real spend, with a simulated PM exercise for comparison
ACTUAL CASH OUTLAY
≈ $36 AUD
Google Colab Pro subscription (≈$12/month × 3 months).
Everything else is open-source or free academic-tier access.
OPEN-SOURCE FIRST PROCUREMENT
SILO & TERN API access
Free · CC BY 4.0 · Required: Before Sprint 2
Google Colab Pro (GPU)
≈$12 AUD/month · Required: Before Sprint 4
GitHub + DVC storage
Free · education plan · Required: Before Sprint 1
Chronos-2 / TimesFM weights
Free · Apache 2.0 · Required: Before Sprint 4
SIMULATED COMMERCIAL BUDGET
(PMBOK cost-management exercise — not real spend)
Chart: 
| Model Dev | Planning | Data Eng. | Integration | Closeout
AUD | 5500 | 4000 | 3200 | 3000 | 2000
Note: The $17,700 figure represents simulated labour-hour costs at notional industry rates — a PMBOK-style cost-baseline exercise from Assessment 1, not an actual invoice.
DeepMoisture • ITEC630 • Team SANSS
15 / 18

## Slide 17
Why We Also Built an MVP
ITEC630 grades the plan — but we wanted proof the plan is buildable
Why bother with an MVP when this course is about project management? Because a plan you can't execute is just a wish-list. Building an MVP lets us de-risk every technical assumption in the PMP.
Validates Risk Estimates
If GPU memory blows up in MVP testing, we know exactly where to harden Sprint 5 — before it becomes a real-deadline crisis.
Confirms Feasibility
Running Chronos-2 zero-shot on a single MDB station proves the foundation-model approach works on our actual data, not just paper benchmarks.
Strengthens Stakeholder Trust
A live demo, however rough, is more persuasive than 30 pages of plans. Supervisors see we'll deliver — and so do we.
MVP SCOPE — what's already built
✓ SILO data extraction script (single station) ✓ ARIMA baseline trained ✓ Chronos-2 zero-shot output
✓ Streamlit dashboard skeleton ✓ GitHub repo + Jira board live ✓ KGE/RMSE evaluation script
DeepMoisture • ITEC630 • Team SANSS
16 / 18

## Slide 18
Why We Also Built an MVP
data extraction script (script
DeepMoisture • ITEC630 • Team SANSS
16 / 18

## Slide 19
Key Takeaways
If you remember five things, remember these
01
Genuine novelty
First rigorous benchmark of Chronos-2 and TimesFM 2.5 on Murray-Darling Basin soil-moisture data.
02
Hybrid methodology
Agile sprints provide rhythm; CRISP-DM phases provide scientific rigour. Best of both worlds.
03
Proactive risk plan
GPU limits, API downtime, model underperformance — each has a concrete mitigation already in place.
04
Five-person team, clear roles
PM, Data, Software, Quality, Comms — no overlap, no gaps, every sprint owned.
05
Ethical alignment
ACS Code of Ethics + environmental stewardship: optimise water use for farmers, not commercial extraction.
Every drop counts. AI helps us count them.
DeepMoisture • ITEC630 • Team SANSS
17 / 18

## Slide 20
THANK YOU
Questions?
We'd love your feedback.
WE'D APPRECIATE YOUR INPUT ON:
Scope realism
Is our scope ambitious yet achievable in 14 weeks?
Risk coverage
Are there technical risks we're missing for foundation models?
Stakeholder reach
Should we engage MDB farmers earlier in user testing?
Evaluation metrics
Are KGE/RMSE the right yardsticks — or should we add CRPS?
Team SANSS • ITEC630 • Australian Catholic University • Semester 1 2026